## Slide 1
CC Power Board Meeting
Discussion Slides
April 22, 2026

## Slide 2
7B. Consideration of 2026-2027 Work Plan and Budget

## Slide 3: Today's Goals
Explain
Receive Feedback
Consider passage or specify further work
Thank you to Budget Ad Hoc Committee
  Rob Shaw, 3CE
  Mitch Sears, VCE
  Monica Padilla, SVCE
  Shawn Marshall, PCE
Agenda Item 7B

## Slide 4: Work-Planning and Budgeting Timeline
Feb
March
May
April
Member Meetings
Board Budget Ad Hoc
Board Consideration/Adoption
Finalizing Work-Plan
Work Planning
Budget Ad
Board Actions
Procurement Directors Meeting
Agenda Item 7B
Member Input
Baseline Work-Plan
Baseline Budget

## Slide 5: Context
Frames: Project-based budget, full year ‘all-in’ picture, differentiate incremental approval amounts
Maturation:
  3 projects COD within 15 months (schedule)
  Established structures: Board meetings, working groups, sub-committees, policies and procedures, etc.
Alignment to Strategic Priorities and Policies
  Strategic Priorities (R.25-12-01): Procurement, Emerging Tech, Asset Ownership, Project Execution
  Policies: Budget (R.24-02-01), Working Capital & Carryover (R.25-11-02)
Agenda Item 7B

## Slide 6: Work Plan: 2026-2027 Budget
Agenda Item 7B
 | Existing Authorized | Annually Authorized
Phase 3 | Tumbleweed (operational, long duration lithium-ion storage) Fish Lake (2027 COD, geothermal) Ormat (2027 COD, geothermal) Willow Rock (2030 COD, compressed air energy storage) | Recurring Phase 3s (bulk-buys, subscription services, computer trainings)
Phase 2 | Expected for Approval in May 2026: Solar + Storage #1 Solar + Storage #2 Geothermal | Geothermal Strategic Origination (extension) Geothermal PPA Geothermal/Emerging Tech PPA Asset Ownership Entry Strategy
Phase 1 | N/A | All-member solicitation and related negotiations 3 Research and Education efforts
G&A | N/A | Annual G&A

## Slide 7: 2025-2026 Draft Recommended Budget
Agenda Item 7B
Summary:
  Expenses: $24.91M
  Market Revenues: $5.12M
  Net Expenditures: $19.79M
 | Existing Authorized ($M) | Annually Authorized ($M) | Total ($M)
Phase 3 | $21.33 | $0.18 | $21.51
Market Revenues (Phase 3) | ($5.12) | $- | ($5.12)
Phase 2 | $0.82 | $0.64 | $1.46
Phase 1 | $0 | $0.35 | $0.35
G&A | $0 | $1.60 | $1.60
Total | $17.03 | $2.77 | $19.79

## Slide 8: Total Budget by Member
Agenda Item 7B
Overall Budget by Phase / Cost Type (000s) | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
Phase 3: PPA/ESSA Payments | $- | $- | ($3,252) | ($3,987) | ($733) | ($2,622) | ($4,512) | ($4,303) | ($840) | ($20,250)
Phase 3: PPA/ESSA Revenues | $- | $- | $822 | $1,008 | $185 | $663 | $1,141 | $1,088 | $212 | $5,120
Phase 3: All Other Project Costs | ($114) | ($24) | ($199) | ($242) | ($64) | ($113) | ($241) | ($200) | ($60) | ($1,257)
Phase 2 Costs | ($264) | ($401) | ($201) | ($80) | ($28) | ($99) | ($194) | ($173) | ($16) | ($1,456)
Phase 1 Costs | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($352)
G&A | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($1,596)
Total1 | ($594) | ($642) | ($3,046) | ($3,518) | ($857) | ($2,387) | ($4,022) | ($3,805) | ($921) | ($19,792)
1. Totals reflect actual numbers. Rounded numbers in this table may lead to slight discrepancies.

## Slide 9: Incremental Approval Amount1
Agenda Item 7B
Overall Budget by Phase / Cost Type (000s)2 | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
Phase 3: All Other Project Costs | ($114) | ($24) | ($199) | ($242) | ($64) | ($113) | ($241) | ($200) | ($60) | ($1,257)
Phase 2 Costs | ($264) | ($401) | ($201) | ($80) | ($28) | ($99) | ($194) | ($173) | ($16) | ($1,456)
Phase 1 Costs | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($352)
G&A | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($1,596)
Total1 | ($594) | ($642) | ($617) | ($539) | ($309) | ($428) | ($651) | ($590) | ($293) | ($4,662)
Removing Power Contract Costs and Revenues
1. Removes Phase 3 Power project pass-through amounts and rev estimates which members have already approved.
2. Totals reflect actual numbers. Rounded numbers in this table may lead to slight discrepancies.

## Slide 10: Carryovers Impacts
 | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE
Estimated Carryover (000s)1 | $303 | $179 | $182 | $131 | $224 | $144 | $252 | $173 | $216
Agenda Item 7B
Budget Components (000s) | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
Total Budget (Slide 8) | ($594) | ($642) | ($3,046) | ($3,518) | ($857) | ($2,387) | ($4,022 | ($3,805) | ($921) | ($19,792)
Incremental Approvals (Slide 9) | ($594) | ($642) | ($617) | ($539) | ($309) | ($428) | ($651) | ($590) | ($293) | ($4,662)
Carryover can be applied in limited ways to reduce invoices for upcoming fiscal year (R.25-11-02).
Members should assume some carryover amounts stays within project accounts – see PABS for more information.
Generalized carryover calculations use forecasts and do not include the Tumbleweed Operating Account deposit amounts and have other manual adjustments.
Totals reflect actual numbers. Rounded numbers in this table may lead to slight discrepancies.

## Slide 11: Year over Year (YOY) Summary
Cost Increases:
Full Year of power project operations
Prior year revenues included settlement
Cost Decreases:
Smaller scope
Reduced contingency
No accumulation of working capital
Agenda Item 7B

## Slide 12: YOY Changes by Member
Drivers:
Phase 3 - more operations, changing use of computer trainings & bulk-buys
Phase 2 project interests
Phase 1 scope, cost management
Change from 2025-26 to 2026-27 Budget |  |  |  |  |  | Negative Numbers represent a YOY Increase |  |  |  | 
Excluding Power Contracts/Revenues: Overall Budget by Phase / Cost Type (000s) | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
Phase 3: Non-Contract/Other Project Costs | $(35) | $(12) | $(49) | $(91) | $(3) | $8 | $(56) | $(31) | $5 | $(265)
Phase 2 Costs | $(5) | $(270) | $(36) | $31 | $109 | $3 | $(21) | $(130) | $88 | $(231)
Phase 1 Costs | $51 | $51 | $51 | $51 | $51 | $51 | $51 | $51 | $51 | $459
G&A | $(3) | $(3) | $(3) | $(3) | $(3) | $(3) | $(3) | $(3) | $(3) | $(30)
Total | $8 | $(234) | $(38) | $(13) | $154 | $59 | $(30) | $(114) | $140 | $(68)

## Slide 13: Cost Management & Staffing
Discretionary spending based on project ‘go/no-gos’ and work-scope
Discretion in FTE and consultant use
  Flat YOY number of staff and recurring consultants
  Areas of cost increases: inflation, staffing for more of the year, expanding accounting needs

## Slide 14: Operating Account Deposits for 2027
Per member-approved contracts, CC Power ‘seeds’ project operating accounts 90-days prior to COD. Members may want visibility to invoice timing.
 | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
Spring 2027 Phase 3 Operating Account Charges (Cash Calls) | ($811k) | $- | ($631k) | ($775k) | ($136) | ($508k) | ($837k) | ($608k) | ($157k) | ($4,464k)
Agenda Item 7B

## Slide 15
Invoicing Plan
Type | Amount | Timing
G&A | Full Amount | Following Budget Approval
Phase 1 | Full Amount | Following Budget Approval
Phase 2 | Full Amount net of any applied carryover amounts | Following Budget Approval and close of Fiscal Year, finalizing carryover amounts
Phase 3 | Per authorized project or contracts net of applied carryover | Per project agreement
Agenda Item 7B

## Slide 16: Tumbleweed Annual Budget
Board approval of Tumbleweed-specific budget is required
  Included in this overall budget
  Separate Board vote recommended
  Detailed budget on next slide
Agenda Item 7B

## Slide 17: Tumbleweed Project Budget by Member
Per PPSA, Project Participants must approve project-specific Annual Budget
Line Item | Total | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | % of Total OpEx | % of Total Cost
Market Revenues | $5,119,758 | $0 | $0 | $822,233 | $1,008,080 | $185,335 | $663,009 | $1,140,682 | $1,087,949 | $212,470 |  | 
Contract Costs | ($20,250,000) | $0 | $0 | ($3,252,150) | ($3,987,225) | ($733,050) | ($2,622,375) | ($4,511,700) | ($4,303,125) | ($840,375) |  | 98.0%
Gross Income | ($15,130,242) | $0 | $0 | ($2,429,917) | ($2,979,145) | ($547,715) | ($1,959,366) | ($3,371,018) | ($3,215,176) | ($627,905) |  | 
Insurance | ($40,249) | $0 | $0 | ($6,464) | ($7,925) | ($1,457) | ($5,212) | ($8,968) | ($8,553) | ($1,670) | 9.5% | 0.2%
Other Operating Expenses | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | 0.0% | 0.0%
Personnel | ($135,166) | $0 | $0 | ($21,708) | ($26,614) | ($4,893) | ($17,504) | ($30,115) | ($28,723) | ($5,609) | 32.0% | 0.7%
Professional: Accounting | ($5,700) | $0 | $0 | ($915) | ($1,122) | ($206) | ($738) | ($1,270) | ($1,211) | ($237) | 1.3% | 0.0%
Professional: Legal | ($7,500) | $0 | $0 | ($1,205) | ($1,477) | ($272) | ($971) | ($1,671) | ($1,594) | ($311) | 1.8% | 0.0%
Professional: Marketing & IT | ($17,475) | $0 | $0 | ($2,806) | ($3,441) | ($633) | ($2,263) | ($3,893) | ($3,713) | ($725) | 4.1% | 0.1%
Professional: Other Misc. | ($211,828) | $0 | $0 | ($34,020) | ($41,709) | ($7,668) | ($27,432) | ($47,195) | ($45,013) | ($8,791) | 50.2% | 1.0%
Travel and External Engagement | ($4,394) | $0 | $0 | ($706) | ($865) | ($159) | ($569) | ($979) | ($934) | ($182) | 1.0% | 0.0%
Operating Costs | ($422,312) | $0 | $0 | ($67,823) | ($83,153) | ($15,288) | ($54,689) | ($94,091) | ($89,741) | ($17,526) | 100.0% | 100.0%
Net Income (Costs) | ($15,552,554) | $0 | $0 | ($2,497,740) | ($3,062,298) | ($563,002) | ($2,014,056) | ($3,465,109) | ($3,304,918) | ($645,431) |  | 

## Slide 18: Ad Hoc Comments and Discussion
Receive Feedback
Consider passage or specify further work
Draft Motions (next slide)
Agenda Item 7B

## Slide 19: Draft Motion Language
Motion #1 (Tumbleweed Members Only): Motion for Tumbleweed Project Members to Approve Draft Recommended 2026-2027 Budget to address Tumbleweed Project Annual Budget requirements per Project Participation Share Agreement, per Agenda Item 7B Memo Appendix B
Motion #2: Motion to approve Draft Recommended 2026-2027 Budget as shown in the Agenda Item 7B Memo (Tables 3, 4, and 9)
Agenda Item 7B

## Slide 20: Supplemental Budget Slides
Agenda Item 7B

## Slide 21: YOY by Accounting Category
Agenda Item 7B
Item | 2026-2027 | 2025-2026 | % Difference
Revenues |  |  | 
Market / Counterparty Project Revenues | $5,119,758 | $6,135,848 | -17%
Expenses |  |  | 
A. ESSA and PPA Expenses | $20,250,000 | $4,218,750 | 380%
B. Personnel | $1,972,036 | $1,859,238 | 6%
C. Professional Services | $2,221,054 | $2,293,260 | -3%
D. Other Operating Expenses | $468,617 | $1,087,048 | -57%
Total Expenses (A+B+C+D) | $24,911,707 | $9,458,296 | 163%
Net Expenditures (II – I) | $19,791,949 | $3,322,448 | 496%
Chart: YOY Accounting Categories
| Market / CounterParty Revenues | ESSA and PPSA Expenses | Personnel | Professional Services | Other Operating Expenses
2026-2027 | 5199758 | 20250000 | 1972036 | 2221054 | 468617
2025-2026 | 6135848 | 4218750 | 1859238 | 2293260 | 1087048
Other Operating Expenses down reduced based on prior year scope, reduced contingency, small recategorizations
Personnel count flat; cost increase due to staff working more during the year vs. prior year

## Slide 22: Annually Authorized by Member
Scope: G&A, 3 research & education projects, all-member solicitation and PPA negotiations, 4 Phase 2 projects, data set and report bulk buys, computer-based trainings
Reflects potential participation – members must still opt in to projects
Agenda Item 7B
Annually Authorized Projects (000s) | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
G&A | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($177) | ($1,596)
Phase 1 Costs | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($39) | ($352)
Phase 2 Costs | ($138) | ($195) | ($75) | ($45) | ($7) | ($28) | ($57) | ($76) | ($16) | ($636)
Phase 3 Costs | ($24) | ($24) | ($24) | ($24) | ($24) | ($2) | ($17) | ($24) | ($17) | ($182)
Total Net Benefits (Expenses) | ($379) | ($436) | ($316) | ($285) | ($248) | ($247) | ($290) | ($317) | ($250) | ($2,766)

## Slide 23: Existing Authorized by Member
Scope: 4 Phase 3 projects, 3 Phase 2s
Reflects expected or known participation – phase 2s to activate in May 2026
Agenda Item 7B
Existing Authorized (000s) | 3CE | Ava | CPSF | PCE | RCEA | SCP | SJCE | SVCE | VCE | Total
PPA/ESSA Payments | $- | $- | ($3,252) | ($3,987) | ($733) | ($2,622) | ($4,512) | ($4,303) | ($840) | ($20,250)
PPA/ESSA Revenues | $- | $- | $822 | $1,008 | $185 | $663 | $1,141 | $1,088 | $212 | $5,120
All Other Existing Authorized Costs | ($215) | ($206) | ($301) | ($253) | ($61) | ($181) | ($361) | ($273) | ($43) | ($1,895)
Total Net Benefits (Expenses) | ($215) | ($206) | ($2,731) | ($3,233) | ($609) | ($2,141) | ($3,732) | ($3,488) | ($671) | ($17,026)

## Slide 24
7C. Fall Member Forum

## Slide 25: 2026 Member Forum – In Person
October 29, 2026
  Noon – 5pm: Meeting
  5pm – 8pm: Reception and Board Dinner
Location: SVCE Offices, Sunnyvale, CA
Agenda: will be provided and noticed
  Enable discussion of Key Topics
Target Audience – Board Members
Agenda Item 7C

## Slide 26
7D. General Manager Report

## Slide 27: Upcoming Phase 2s
All-member RFO yielding several project pursuits, pursuing exclusivity
All other projects released from further consideration / holds
Target launch of any Phase 2s in May 2026
  Members may apply unallocated Phase 2 funds
Agena Item 7D

## Slide 28: Tumbleweed – Status Update
75 MW / 8-hour battery project (overall project is 125 MW)
  Expected Commercial Operation Date (COD): June 1, 2026
  Expected to be first 8-hr battery in CAISO
Project on track:
  Site inspection completed and confirmed aligned w/ ESSA
  Notice of Expected COD per ESSA
  Completed CAISO Capacity Test and ESSA’s Commercial Operation Capacity Test
  RA Supply Plan submitted to CAISO and CPUC
  CAISO Commercial Operations on March 30, 2026
  Updated Letters of Credit for Performance Assurance in progress
Agena Item 7D

## Slide 29: Tumbleweed - Operations Preparation
Operating Account funded
Budgeted through CC Power annual budget
Operations Advisory Subcommittee approved procedures:
  Resource Adequacy
  Outage Management
  New Resource Implementation
In progress procedures:
  Settlements
    Planning dry-run of Settlements process prior to first monthly invoice
  Scheduling & Bidding
Agena Item 7D

## Slide 30: Tumbleweed – Scheduling and Bidding Preparation
Scheduling Coordinator
  Vendor Selection and Contracting
  Secured CAISO User Access
  Provisioned into Tenaska’s PowerTools Platform
  Negotiated TPS Parent Guarantee – need signatures
Market Bidding
  Vendor Selection and Contracting
  Backcast analysis – in progress
  Strategy for risk tolerance – in progress
  Bidding strategies – in progress
Agena Item 7D

## Slide 31: Tumbleweed Ribbon Cutting
Ribbon Cutting: June 18, ~ 11:00 am-2:00 pm
  Location: Rosamond, CA (Kern County)
  Draft Agenda:
    10:45 Arrival
    11:-00 Speakers (REV, off-takers [CC Power ~5 mins], CPUC, state/county/local officials)
    11:30 Lunch & Networking
    12:30-2:00 Site tours, photo ops, continued networking
  REV leading outreach and invitations
  CC Power coordinating with participating members' marketing teams
  Interested in attending? – RSVP to CC Power (if you have not already)
Agena Item 7D

## Slide 32: Other Project Updates
Ormat Portfolio (up to 125 MW of geothermal)
  Crescent Valley (NV 25 MW geo) no longer indicated by Ormat for potential portfolio inclusion
Hydrostor – Willow Rock (50 MW / 400 MWh compressed air storage)
  Development Security received and accepted
  Expect all members' approvals by 4/24
  PPSA and BLPTAs to be distributed for member signatures
    Invoices to issue in May for Phase 3 contract management this year (Feb-June)
GEODE Projects w/ Atlantica, XGS, and Zanskar
  Announced execution of agreements
  Exploring opportunities for offtake contracting and need for QC16 IPE points
Agena Item 7D

## Slide 33: Financial Updates
Spending versus Budget:
  Overall, significant underspending versus budget
    Tumbleweed
    Phase 2s
    Federal matters, permitting/external delays
    No new FTEs
  Contract Managements efforts on track
Other Financial Matters:
  Working Capital
  Tumbleweed Operating Account
  Unallocated Phase 2s
Agena Item 7D

## Slide 34
Agena Item 7D
Category | Budget | EOY FCST | Variance ($) | % Utilized
PPA Operations | $4,218,750 | $1,427,000 | $2,791,750 | 33.8%
Legal | $777,700 | $196,849 | $580,851 | 25.3%
Other Professional Services | $1,758,360 | $678,123 | $1,080,236 | 38.6%
Project Overhead | $829,248 | $138,340 | $690,908 | 16.7%
Personnel | $1,874,238 | $1,572,205 | $302,033 | 83.9%
Total With PPA Operations | $9,458,296 | $4,012,518 | $5,445,778 | 42.4%
Total Excluding PPA Operations | $5,239,546 | $2,585,518 | $2,654,028 | 49.3%
Budget vs Actual – Summary Spending Forecast for EOY
Forecast – Actuals will Differ

## Slide 35: Budget vs Actual – Non-Project and Project Spending Forecast for EOY
Agena Item 7D
Non-Project (G&A & Phase I) | Budget | Actual | Variance | % Used
Legal | $272,200 | $78,636 | $193,564 | 28.9%
Other Prof. Svcs | $537,077 | $281,705 | $255,372 | 52.5%
Project Overhead | $497,243 | $72,913 | $424,330 | 14.7%
Personnel | $1,020,037 | $921,982 | $98,055 | 90.4%
TOTAL | $2,326,557 | $1,355,236 | $971,321 | 58.3%
All Projects | Budget | Actual | Variance | % Used
Legal | $505,500 | $118,214 | $387,286 | 23.4%
Other Prof. Svcs | $1,221,282 | $396,418 | $824,864 | 32.5%
Project Overhead | $332,005 | $65,427 | $266,578 | 19.7%
Personnel | $854,201 | $650,223 | $203,978 | 76.1%
TOTAL | $2,912,988 | $1,230,282 | $1,682,706 | 42.2%
Chart: % EOY Forecast of Budget Utilized Select Items
| Tumbleweed | Fish Lake | Ormat Portfolio | Willow Rock | Geo Pursuits | G&A and Phase 1
% Budget Utilized by Project | 0.926 | 0.913 | 0.879 | 1 | 0.397 | 0.583
Forecast – Actuals will Differ

## Slide 36: Strategic Plan Update
Agenda Item 7D
*Estimated Plan – Board and Officers may further direct.
Updates in progress
  Goals, Trajectory, and Milestones for 2026-2030
  Four Priorities (R.25-12-01)
Aligns with Draft Recommended 2026-2027 Budget
  Focus
  Sequenced to support longer-term plans
Board Discussion of Plan (May)

## Slide 37: General Manager Activity
Completed Phase 1 Transmission Education Project w/ ZGlobal
Commenced P1 Emerging Tech Exploration focused on clean firm resource tech
Executed Agreements
    1/15/2026 – Gridwell Cost Sharing Agreement Confirm
    1/29/2026 – XGS GEODE Agreement
    1/29/2026 – Atlantica GEODE Agreement
    1/29/2026 – Wood Mackenzie Cost Sharing Agreement Confirm
    2/4/2026 – Hydrostor RA+TB4
    2/12/2026 – Tenaska Power Services Bulk Pricing Letter Agreement
    2/18/2026 – GridSME Master Services Agreement and two Scopes of Work
    SOW #1 – Not to exceed $15,000 (Tumbleweed onboard)
    SOW #2 – $5,018 (site inspection, owner’s engineer verification of installation)
    3/1/26 – Office Sublet, Biering and Brown
    3/10/2026 – Zanskar GEODE Agreement
    3/12/2026 – Employment Agreement w/ Katrina Haidari for Graduate Associate Internship
Agenda Item 7D